## ProjectSchedule
Priority titles |  | ► Watch How to Make a Gantt Chart in Excel
Cochrane Fertility Regulation
| Start date | Protocol publication | Review publication
TASK
Title registration
Treatments of unscheduled vaginal bleeding from hormonal contraception | expected December, 2021
Protocols
Self- & out-patient management of abortion follow-up after 20-weeks gestation’ (T0113) | May, 2019 | expected December, 2021
Perioperative antibiotics versus no antibiotics to prevent infection after surgical abortion (T0115) | September, 2019 | expected February, 2022
Impact of abortion laws and policy on access, safety and health outcomes (T0118) | July, 2019 | expected February, 2022
Immediate versus delayed postabortal initiation of short acting birth control (C0120) | April, 2020 | expected February, 2022
Doctors or mid-level providers for abortion (T0096, update review) | July, 2019 | expected May, 2022
Reviews
Pain management for medical abortion before 14 weeks gestation (T0112) | April, 2019 | January, 2020 | expected December, 2021
Strategies for treatment of heavy bleeding or pain associated with intrauterine device use (C0052, update review) | December, 2019 | original review September, 2011 | expected January, 2022
Immediate versus delayed postpartum insertion of contraceptive implant and IUD for contraception (C0101) | February, 2020 | original review, April 2017 | expected January, 2022
Cervical preparation for second trimester dilation and evacuation (T0059, update review) | May, 2019 | original review June, 2010 | expected March, 2022
Surgical versus medical methods for second trimester induced abortion (T0057, update review) | November, 2019 | original review, April 2008 | expected March, 2022
Progestin IUDs versus Copper IUDs for emergency contraception (C0122) | December, 2019 | October, 2020 | expected March, 2022
Interventions to improve access to medical abortion (e.g. self-administration, teleabortion) (T0114) | June, 2019 | November, 2020 | expected March, 2022
Medical Methods for abortions 13 weeks and above (T0119) | May, 2020 | December, 2020 | expected March, 2022
Hormonal contraceptive use and depression (C0125) | August, 2020 | January, 2021 | expected March, 2022
Risk of thromboembolism in patients with COVID-19 who are using hormonal contraception (C0126) | September, 2020 | March, 2021 | expected March, 2022
Interventions for vaginal bleeding irregularities with contraceptive implant (C0117) | July, 2019 | March, 2021 | expected May, 2022
Steroidal contraceptives: effect on carbohydrate metabolism in women without diabetes mellitus (C0054, update review) | October, 2019 | original review April, 2014 | expected July, 2022
Contraceptives methods for contraception in overweight or obese women (C0069, update review) | October, 2019 | original review, August 2016 | expected July, 2022
Combined hormonal versus non-hormonal versus progestin-only contraception in lactation (C0036, update review) | January, 2020 | original review, March 2016 | expected July, 2022
Continuous or extended cycle vs. cyclic use of combined hormonal contraceptives for contraception (C0040, update review) | November, 2019 | orignal review, July 2014 | expected July, 2022
Published
Self-administration versus provider administration of medical abortion (T0108) | October, 2017 | November, 2018 | February, 2020
Insert new rows ABOVE this one
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
► Watch How This Gantt Chart Was Created
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.